## Sheet1
UTILITY COORDINATION STATUS REPORT
Project No.: |  |  | Designer: |  |  |  |  | Contractor:
Project Name: |  |  | Contact: |  |  |  |  | Contact:
DPW DM: |  |  | Phone: |  |  |  |  | Phone:
DPW CM: |  |  | e-mail: |  |  |  |  | e-mail:
|  | 811 Utility Research Completed (DPW Utility Coordinator) | Initial Notice | Verification Letter & Conflict Analysis (50%) Plans | Field Check/ Coordination Meeting | Preliminary Final (95%) Plans & Work Plan Request | Utility Work Plans Due | Rerun Indiana 811 Design Ticket | Create Gantt Chart | Final (100%) Plans | Pre-Bid | Bid Date | Pre-Con | Utility NTP | Contractor NTP
TARGET DATE
ACTUAL/SENT DATE
UTILITY RESPONSE DUE
REMINDER SENT
Utility | Contact | e-mail | Phone | Initial Notice Response | Facilities in Project Area? (Y/N) | Existing Facilities Verification & Conflict Response | Conflicts? (Y/N) | Relocation Required? (Y/N) | URA Required? (Y/N) | URA Status (Pending/Approved) | Work Plan Received | Cost Estimate for Relocation | Work Plan Approved | NTP Sent to Utility | URA Sent to Utility
Y
N
NOTES: